## Risk log
Risk Reference | Date Raised | Risk Response | Area (Function) | Risk Description | Probability | Impact | Probability Score | ImpactScore | RiskScore | Risk Rating | Escalation Level | Status | Mitigation | Key mitigation actions / Closure note | Monitor Date | Closed Date | Closed By | Comments
R-ST2 | 2026-01-05 | Reduce | Delivery | There is a risk that the NetSuite / ProScope siloed approach to UAT will not demonstrate an integrated E2E solution. | Unlikely | Moderate | 2 | 3 | 7 | Medium |  | In Progress | E2E Test phase added to plan; Stonbury to develop E2E test cases for super users, |  | 2026-01-05
R-ST5 | 2026-01-05 | Accept | Delivery | There is a risk that ProScope dev completion by 06 Feb is a critical path dependency. Any delay affects data model freeze. | Almost Certain | Moderate | 5 | 3 | 22 | High |  | In Progress | Go/No go RACI and checklist as well as a Go/No Go checkpoint | Track WS5.D dates daily; contingency needed.
R-ST7 | 2026-01-05 | Accept | Delivery | There is a risk that if the End-state data model is not confirmed there will be a knock-on risk to ETL rebuild timeline (WS5.D) | Unlikely | Major | 2 | 4 | 12 | Medium |  | In Progress | Ensure NetSuite signs off any config work | Lock architecture with vendors by 12 Feb. Closed Kamran reviewing end 2 end data attributes supported by Mohit
R-ST8 | 2026-01-05 | Accept | Delivery | There is a risk that DWH SIT Test Load Cycle may fail if DWH jobs or transformations aren't stabilised. | Possible | Major | 3 | 4 | 18 | High |  | In Progress | Alignment cadence meetings scheduled | Early technical trial
R-ST9 | 2026-01-05 | Accept | Delivery | There is a risk that UAT participants will not receive formal training, relying on SOPs there may be negative quality/timescales impacts | Possible | Moderate | 3 | 3 | 14 | Medium |  | Open | SMEs to be available to support UATers |  | 2026-06-04
R-ST10 | 2026-03-13 | Reduce | Delivery | There is a risk that multiple users/activities in a single environment may cause conflicts/delays. | Likely | Major | 4 | 4 | 21 | High |  | Open | Coordination controls, sequencing rules, naming conventions, user guidance Consideration on a separate environment for testing |  | 2026-04-17
R-ST11 | 2026-03-13 | Accept | Delivery | There is a risk that Training support may reduce due to cutover priorities | Unlikely | Major | 2 | 4 | 12 | Medium |  | In Progress | Monitor only |  | 2026-04-24
R-ST12 | 2026-03-13 | Reduce | Delivery | There is a risk that delays in training during cutover could create operational challenges. | Possible | Moderate | 3 | 3 | 14 | Medium |  | In Progress | Extend the Go live date |  | 2026-01-05
R-ST13 | 2026-03-13 | Reduce | Delivery | There is a risk that after NetSuite UAT sign‑off, NetSuite supports only Training & Cutover therefore there is an unclear mechanism for resolution of any defects found that create go-live risks | Almost Certain | Moderate | 5 | 3 | 22 | High |  | In Progress | Contractual NetSuite options available. |  | 2026-04-24
R-ST14 | 2026-03-13 | Reduce | Delivery | There is a risk that the extension to the Go-live date may lead to vendor constraints or Change Requests (NetSuite SOW ends 29/5). | Possible | Moderate | 3 | 3 | 14 | Medium |  | In Progress | Commercial contract under review |  | 2026-04-24
R-ST16 | 2026-03-13 | Reduce | Delivery | There is a risk that the super users /users will not be available for training due to the Easter period | Unlikely | Major | 2 | 4 | 12 | Medium |  | In Progress | Circulate training materials, SOP's and training schedule ahead of time |  | 2026-04-30
R-ST17 | 2026-03-13 | Reduce | Delivery | There is a risk of delivery due to Go‑live being close to bank holidays & month‑end workload. | Unlikely | Major | 2 | 4 | 12 | Medium |  | Open | Revised timelines published; Sufficient timescales for resource plans to be put in place
R-ST18 | 2026-03-13 | Reduce | Delivery | The data load into sandbox for testing/validation may is not sufficient to meet plan needs due lack of clarity on plan and responsibilities across multiple vendors. | Likely | Major | 4 | 4 | 21 | High |  | In Progress | Project team to define approach; aligns with sandbox tidy‑up plan additions. |  | 2026-03-04
R-ST19 | 2026-03-13 | Reduce | Delivery | There is a risk that the Template completeness/coverage will not be approved before production. | Likely | Major | 4 | 4 | 21 | High |  | In Progress | Project Team to review source data & test template coverage. |  | 2026-04-30
R-ST20 | 2026-03-13 | Reduce | Delivery | There is a risk that there will be a significant proportion of users untrained at Go-live | Possible | Major | 3 | 4 | 18 | High |  | Open | Training extended to 4 weeks in revised plan. Training completion to be reviewed at steering boards |  | 2026-04-24
R-ST21 | 2026-03-13 | Reduce | Delivery | There is risk that the Internal IT team will not have the capability to manage/support ERP system from go-live and embedded required changes | Likely | Major | 4 | 4 | 21 | High |  | In Progress | ERP Help and Support desk resource model to be agreed and mobilised |  | 2026-04-24
R-ST22 | 2026-03-13 | Reduce | Delivery | There is a risk that cutover process and rollback ownership is not clearly defined and communicate | Likely | Major | 4 | 4 | 21 | High |  | In Progress | NetSuite delivery methodology controls cutover and a workshop to establish clear RACI across vendors |  | 2026-04-24
R-ST23 | 2026-03-13 | Prevent | Delivery | There is a risk that the high degree of custom configuration will impact upgrades in future | Likely | Major | 4 | 4 | 21 | High |  | In Progress | Ensure NetSuite signs off any config work |  | 2026-04-24

## Issue Log
Issue number | Project | Area (Function) | Associated risk number | Status | Owner | Business Owner | Date raised | Issue description | Priority | Resolution approach | Assigned To | Due Date | Comments
I-ST5 | Stonbury ERP Programme Transformation | Delivery | R-ST18 | Open | Steve Grice | Richard Ward | 16/03/2026 | The data load activities are not sufficiently mature to meet the project outcomes due to lack of clarity on activities and responsibilities across multiple parties. | High | Define activities needed to support business outcomes. Individual and Group discussions as needed. Establish accountabilities/responsibilities and gain commitment for key activities (Sandbox and Cutover) Add to plan and manage |  |  | 2026/03/18 - Discussions with Panamoure/Stonbury to clarify knowledge of DWH, Templates and source data needs
I-ST6 | Stonbury ERP Programme Transformation | Delivery | R-ST15 | Open | Steve Grice | Richard Ward | 16/03/2026 | There is no defined plan in place for the creation of reports for go‑live/initial month‑end needs | High | Define activities needed to support business outcomes. Individual and Group discussions as needed. Establish accountabilities/responsibilities and gain commitment for all reports at a timing required (UAT/Go-Live/Month End/Board) Add to plan and manage |  |  | 2026/03/18 - Detailed tracking commenced; Clarification of needs, timescales and data needs underway; Panamoure have commenced scoping of PowerBi custom reports. Discussions with other report creators (ProScope/ACS/Stonbury team ...) to be scheduled

## Assumptions Log
Number | Project | Area (Function) | Assumption | Raised by | Date raised | Status | Comments
A-ST1 | Stonbury ERP Programme Transformation | Delivery | Super‑users are equiped and knowledgeable to train other Stonbury users on demand | Innocent Khumalo | 2026-01-05 | In Progress | It is critical that the super users across the business are identified, available, and able to support testing, training and go-live
A-ST2 | Stonbury ERP Programme Transformation | Delivery | Draft SOPs are “good enough” for training | Innocent Khumalo | 2026-01-05 | In Progress | Plan has review cycles to validate fit for purpose
A-ST3 | Stonbury ERP Programme Transformation | Delivery | The NetSuite delivery methodology enable Roles and Responsibilities to be clearly defined to enable all Vendors to provide support during cutover and hyper‑care | Innocent Khumalo | 2026-01-05 | In Progress | Post NetSuite UAT NetSuite will progress the planning of the plan outline for cutover they have provided which will clarify RACI
A-ST4 | Stonbury ERP Programme Transformation | Delivery | There will be no scope change post config sign off | Innocent Khumalo | 2026-01-05 | Open | ProScope CR agreed not required so scope for Go-Live should be confirmed 16/3/2026

## Dependencies Log
Number | Project | Description | Raised by | Agreed with impacted parties | Signed off by | Date raised | Status | Comments
D-ST2 | StonburyERPProgrammeTransformation | ProScope solution stability | Stonbury ERP Programme Transformation | Pending |  | 2026-05-03 | Open | Rework & delay
D-ST3 | StonburyERPProgrammeTransformation | Vendors SOWs and contracts support cutover and hyper‑care resourcing | Stonbury ERP Programme Transformation | Pending |  | 2026-05-03 | Open | Prolonged incidents
D-ST4 | StonburyERPProgrammeTransformation | Governance & ownership model sign‑off | Stonbury ERP Programme Transformation | Pending |  | 2026-05-03 | Open | Accountability gaps causing service issues in BAU